## G- Chart
E-BUS PROJECT SCHEDULE under CESL EV Bus Project
Name of State: Maharastra | [15 empty] | Date of approval of PERT Chart:
Name of Bus Depot Project: Backbay Bus Depot | [15 empty] | Name of STA : |  |  | BEST
| Select a period to highlight at right. A legend describing the charting follows. | [14 empty] | Month
Sr No | ACTIVITY | Original Duration | Strat Date | End Date | Actual Start | Actual End | Actual Duration | Delay | Unit | Qty as per scope | Qty executed | Balanced Qty | % of Progress | Weightage | % of activity Completed | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
[16 empty] | 2022-05-01 | 2022-06-02 | 2022-07-03 | 2022-08-04 | 2022-09-05 | 2022-10-06 | 2022-11-07 | 2022-12-08 | 2023-01-09 | 2023-02-10 | 2023-03-11 | 2023-04-12
| First layer | [14 empty] | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 13
| Key Events / Major Milestones | 1: 100; 6: 6=5-4; 7: 7=6-1; 11: 11=9-10 | 1.25% | 100% | 13=12*(10/9)
A1 | Letter of Award reveived from TML
A2 | Site Survey, Job scope finalization and Proposed layout submission | 16 | 1-Dec-2022 | 17-Dec-2022 | 2022-12-02 | 2022-12-20 | 18 | 2 | EA | 1 | 0.5 | 0.5 | 1.25% | 2.5% | 1.25%
A3 | Detailed Engineering for Approval of Civil & Electrical Layout, GA Drawing from TML | 1: 9; 2: 5-Dec-2022; 3: 14-Dec-2022; 7: -9 | 0.0% | 2.5% | #DIV/0!
A4 | Site Mobalization activity Completed | 1: 9; 2: 6-Dec-2022; 3: 15-Dec-2022; 7: -9 | 0% | 5% | #DIV/0!
A5 | Approval of statutory clearances of BUS Depot | 1: 19; 2: 4-Dec-2022; 3: 23-Dec-2022; 7: -19 | 0% | 15% | #DIV/0!
A6 | Procurement of Order Finalisation Completed | 1: 19; 2: 10-Dec-2022; 3: 29-Dec-2022; 7: -19 | 0% | 15% | #DIV/0!
A7 | Receipt of all Materials at Site | 1: 30; 2: 29-Dec-2022; 3: 28-Jan-2023; 7: -30 | 0% | 10% | #DIV/0!
A8 | Civil Infra Development completed at Bus Depot | 1: 95; 2: 12-Dec-2022; 3: 17-Mar-2023; 7: -95 | 0% | 30% | #DIV/0!
A9 | Electrical Infra Development completed at Bus Depot | 1: 65; 2: 24-Dec-2022; 3: 27-Feb-2023; 7: -65 | 0% | 15% | #DIV/0!
A10 | Bus Depot work Completed & Handover to TML | 1: 12; 2: 27-Feb-2023; 3: 11-Mar-2023; 7: -12 | 0% | 5% | #DIV/0!
| Second layer | 7: 0 |  |  | #DIV/0!
A1 | Letter of Intent reveived from TML | 7: 0 |  |  | #DIV/0!
A2 | Site Survey, Job scope finalization and final layout preparation | 7: 0 |  |  | #DIV/0!
1 | Initial survey of Depot with TML & STA Team | 1: 1; 2: 2022-12-01; 3: 01.12.2022; 7: -1 |  | 0.5% | #DIV/0!
2 | Details survey of Depot with TPC Civil & Elecrical team | 1: 1; 2: 02.12.2022; 3: 02.12.2022; 7: -1 |  | 1.0% | #DIV/0!
3 | Survey Report submission with Existing & Proposed Layout Drawings | 1: 2; 2: 03.12.2022; 3: 04.12.2022; 7: -2 |  | 0.3% | #DIV/0!
4 | Job scope finalization & preparation of BOQ | 1: 5; 2: 06.12.2022; 3: 10.12.2022; 7: -5 |  | 0.5% | #DIV/0!
5 | Power Connection/ load applied by STA to Discom | 1: 7; 2: 11.12.2022; 3: 2022-12-17; 7: -7 |  | 0.3% | #DIV/0!
A3 | Detailed Engineering for Approval of Civil & Electrical Layout, GA Drawing from TML | 7: 0 |  |  | #DIV/0!
1 | RFC Drawings of Civil Activities | 1: 10; 2: 2022-12-05; 3: 14.12.2022; 7: -10 |  | 1.5% | #DIV/0!
2 | EV Layout Drawings of Electrical Activities | 1: 8; 2: 07.12.2022; 3: 14.12.2022; 7: -8 |  | 0.7% | #DIV/0!
3 | Shed Lighting Drawings & Specification | 1: 2; 2: 13.12.2022; 3: 2022-12-14; 7: -2 |  | 0.3% | #DIV/0!
A4 | Site Mobalization activity Completed | 7: 0 |  |  | #DIV/0!
1 | Deployment of Civil Man Power | 1: 7; 2: 2022-12-06; 3: 12.12.2022; 7: -7 |  | 1.25% | #DIV/0!
2 | Deployment of Electrical Man Power | 1: 7; 2: 06.12.2022; 3: 12.12.2022; 7: -7 |  | 1.25% | #DIV/0!
3 | Estabilisment of Site Project office | 1: 10; 2: 06.12.2022; 3: 2022-12-15; 7: -10 |  | 2.5% | #DIV/0!
A5 | Approval of statutory clearances of BUS Depot | 7: 0 |  |  | #DIV/0!
1 | Consent to Established-Pollution control board approval | 1: 20; 2: 2022-12-04; 3: 23.12.2022; 7: -20 |  | 1.5% | #DIV/0!
2 | Consent to Operate-Pollution control board approval | 1: 20; 2: 04.12.2022; 3: 23.12.2022; 7: -20 |  | 1.5% | #DIV/0!
3 | Fire NOC for Electrical vehicle charging infrastructure | 1: 20; 2: 04.12.2022; 3: 23.12.2022; 7: -20 |  | 1.5% | #DIV/0!
4 | Chief Inspector of Factory /Director(DISH Approval) | 1: 20; 2: 04.12.2022; 3: 23.12.2022; 7: -20 |  | 1.5% | #DIV/0!
5 | CEIG/EI Approval | 1: 20; 2: 04.12.2022; 3: 23.12.2022; 7: -20 |  | 1.5% | #DIV/0!
6 | Charging Shed Errection Approval | 1: 20; 2: 04.12.2022; 3: 23.12.2022; 7: -20 |  | 1.5% | #DIV/0!
7 | Effluent treatment plant | 1: 20; 2: 04.12.2022; 3: 23.12.2022; 7: -20 |  | 1.5% | #DIV/0!
8 | Soild Waste Managent | 1: 20; 2: 04.12.2022; 3: 23.12.2022; 7: -20 |  | 1.5% | #DIV/0!
9 | ETP Plant | 1: 20; 2: 04.12.2022; 3: 23.12.2022; 7: -20 |  | 1.5% | #DIV/0!
10 | Hazardous waste approval | 1: 20; 2: 04.12.2022; 3: 2022-12-23; 7: -20 |  | 1.5% | #DIV/0!
A6 | Procurement of Order Finalisation Completed | 7: 0 |  |  | #DIV/0!
1 | PR/PO Generation for PSS | 1: 20; 2: 2022-12-10; 3: 29.12.2022; 7: -20 |  | 3.0% | #DIV/0!
2 | PR/PO Generation for Charger | 1: 20; 2: 10.12.2022; 3: 29.12.2022; 7: -20 |  | 3.0% | #DIV/0!
3 | PR/PO Generation for SFU Panel | 1: 20; 2: 10.12.2022; 3: 29.12.2022; 7: -20 |  | 3.0% | #DIV/0!
4 | PR/PO Generation for HT Cable | 1: 20; 2: 10.12.2022; 3: 29.12.2022; 7: -20 |  | 3.0% | #DIV/0!
5 | PR/PO Generation for LT Cable | 1: 20; 2: 10.12.2022; 3: 2022-12-29; 7: -20 |  | 3.0% | #DIV/0!
A7 | Receipt of all Materials at Site | 7: 0 |  |  | #DIV/0!
1 | Delivery of PSS at Site | 1: 90; 2: 2022-12-29; 3: 28.03.2023; 7: -90 |  | 3.3% | #DIV/0!
2 | Delivery of Charger at Site | 1: 90; 2: 29.12.2022; 3: 28.03.2023; 7: -90 |  | 3.3% | #DIV/0!
3 | Delivery of SFU Panel at Site | 1: 30; 2: 29.12.2022; 3: 28.01.2023; 7: -30 |  | 1.1% | #DIV/0!
4 | Delivery of HT Cable at Site | 1: 45; 2: 29.12.2022; 3: 14.02.2023; 7: -45 |  | 1.1% | #DIV/0!
5 | Delivery of LT Cable at Site | 1: 30; 2: 29.12.2022; 3: 2023-01-28; 7: -30 |  | 1.1% | #DIV/0!
A8 | Civil Infra Development completed at Bus Depot | 7: 0 |  |  | #REF!
1 | Concrete breaking | 1: 6; 2: 2022-12-12; 3: 18-Dec-2022; 7: -6 |  | 2.4% | #REF!
2 | Manual Excavation | 1: 6; 2: 18-Dec-2022; 3: 24-Dec-2022; 7: -6 |  | 0.9% | #REF!
3 | Soling | 1: 3; 2: 24-Dec-2022; 3: 27-Dec-2022; 7: -3 |  | 1.1% | #REF!
4 | PCC & Curing | 1: 9; 2: 27-Dec-2022; 3: 5-Jan-2023; 7: -9 |  | 1.5% | #REF!
5 | Reinforcement tying of Raft (charger Foundation) | 1: 12; 2: 5-Jan-2023; 3: 17-Jan-2023; 7: -12 |  | 1.5% | #REF!
6 | Shuttering of Raft (charger Foundation) | 1: 7; 2: 17-Jan-2023; 3: 24-Jan-2023; 7: -7 |  | 1.5% | #REF!
7 | Concreting of Raft (charger Foundation) and Curing | 1: 9; 2: 24-Jan-2023; 3: 2-Feb-2023; 7: -9 |  | 1.5% | #REF!
8 | Reinforcement tying of pedestal (PSS) | 1: 8; 2: 2023-01-05; 3: 13-Jan-2023; 7: -8 |  | 1.5% | #REF!
9 | Shuttering of pedestal (PSS Foundation) | 1: 7; 2: 13-Jan-2023; 3: 20-Jan-2023; 7: -7 |  | 1.5% | #REF!
10 | Concreting of pedestal (PSS Foundation) | 1: 9; 2: 20-Jan-2023; 3: 29-Jan-2023; 7: -9 |  | 6.6% | #REF!
11 | Reinforcement tying of Raft (shed) | 1: 12; 2: 2023-01-05; 3: 17-Jan-2023; 7: -12 |  | 0.6% | #REF!
12 | Shuttering of Raft (shed) | 1: 4; 2: 17-Jan-2023; 3: 21-Jan-2023; 7: -4 |  | 0.6% | #REF!
13 | Concreting of Raft (shed) and Curing | 1: 9; 2: 21-Jan-2023; 3: 30-Jan-2023; 7: -9 |  | 0.6% | #REF!
17 | Backfilling | 1: 2; 2: 30-Jan-2023; 3: 1-Feb-2023; 7: -2 |  | 1.1% | #REF!
18 | Erection of shed structure | 1: 25; 2: 1-Feb-2023; 3: 26-Feb-2023; 7: -25 |  | 1.2% | #REF!
19 | Roof sheeting | 1: 8; 2: 26-Feb-2023; 3: 6-Mar-2023; 7: -8 |  | 1.1% | #REF!
20 | Concreting around excavated area | 1: 9; 2: 6-Mar-2023; 3: 15-Mar-2023; 7: -9 |  | 0.6% | #REF!
21 | Thermoplastic paint | 1: 4; 2: 15-Mar-2023; 3: 19-Mar-2023; 7: -4 |  | 0.3% | #REF!
22 | Crash barrier | 1: 9; 2: 19-Mar-2023; 3: 28-Mar-2023; 7: -9 |  | 0.3% | #REF!
23 | 5S activity | 1: 3; 2: 28-Mar-2023; 3: 31-Mar-2023; 7: -3 |  | 0.3% | #REF!
24 | Cable Trenching (for burried cable) | 1: 8; 2: 31-Mar-2023; 3: 8-Apr-2023; 7: -8 |  | 1.0% | #REF!
25 | Compressor foundation and room | 1: 20; 2: 2023-01-21; 3: 10-Feb-2023; 7: -20 |  | 0.5% | #REF!
26 | DTB Room | 1: 25; 2: 2023-01-21; 3: 15-Feb-2023; 7: -20 |  | 0.5% | #REF!
27 | Road leveling and resurfacing | 1: 20; 2: 15-Feb-2023; 3: 7-Mar-2023; 7: -20 |  | 0.8% | #REF!
28 | Painiting | 1: 10; 2: 7-Mar-2023; 3: 17-Mar-2023; 7: -10 |  | 0.3% | #REF!
A9 | Electrical Infra Development completed at Bus Depot | 7: 0 |  |  | #DIV/0!
1 | Earthing Pit erection with GI Flat | 1: 10; 2: 2022-12-24; 3: 3-Jan-2023; 7: -10 |  | 1% | #DIV/0!
2 | LA Arrangement with GI Flat on charging Shed | 1: 2; 2: 2023-03-06; 3: 8-Mar-2023; 7: -2 |  | 0.2% | #DIV/0!
3 | Installation of PSS | 1: 4; 2: 2023-01-29; 3: 2-Feb-2023; 7: -4 |  | 2% | #DIV/0!
4 | Installation of Charger | 1: 7; 2: 2023-02-02; 3: 9-Feb-2023; 7: -7 |  | 2% | #DIV/0!
5 | Installation of SFU Panel | 1: 1; 2: 2023-02-01; 3: 2-Feb-2023; 7: -1 |  | 0.5% | #DIV/0!
6 | Laying of HT cable Erection | 1: 10; 2: 2023-02-01; 3: 11-Feb-2023; 7: -10 |  | 4% | #DIV/0!
7 | Laying of LT cable Erection | 1: 9; 2: 2023-02-11; 3: 20-Feb-2023; 7: -9 |  | 2.8% | #DIV/0!
8 | Installation of VTPN/SPN DB | 1: 2; 2: 2023-02-20; 3: 22-Feb-2023; 7: -2 |  | 0.5% | #DIV/0!
9 | Installation of Shed Lighting & other arrangement | 1: 3; 2: 2023-02-20; 3: 23-Feb-2023; 7: -3 |  | 1% | #DIV/0!
10 | Commissioning & Testing of Bus Depot | 1: 4; 2: 2023-02-23; 3: 27-Feb-2023; 7: -4 |  | 1% | #DIV/0!
A10 | Bus Depot work Completed
1 | CMS Integration | 1: 5; 2: 2023-02-27; 3: 4-Mar-2023; 7: -5 |  | 0.5% | #DIV/0!
2 | Bus Depot work Completed & Handover to TML | 1: 12; 2: 2023-02-27; 3: 11-Mar-2023; 7: -12 |  | 4.5% | #DIV/0!
Note: Unit & Qty as per scope wiil provide you later